## Summary
Make Ready Report Summary
Job Information
Job Name | Unknown Job
Report Created | 2025-05-15 16:19:20
Statistics
Total Poles | 43
Total Connections | 44
Poles with Proposed Attachments | 9
Poles with Proposed Risers | 2
Poles with Proposed Guys | 9
Notes
1. This report was generated from Katapult JSON data
2. Column headers in the 'Make Ready Report' sheet correspond to field names in the original data

## Make Ready Report
operation_number | attachment_action | pole_owner | pole_number | pole_structure | proposed_riser | proposed_guy | pla_percentage | construction_grade | node_id_1 | node_id_2 | connection_id | span_length | pole_tag_1 | pole_tag_2 | latitude_1 | longitude_1 | latitude_2 | longitude_2 | lowest_com_height | lowest_cps_height | scid_1 | scid_2 | connection_type | mr_status | Remedy Description | Movement Summary | Attachers | Midspan Heights
| (I)nstalling | CPS Energy | 379971 | 40-4 Southern Pine | NO | NO | 83.34% | D | -OJ_PU-d5b_qyvPLb1ox | -OJ_PMjpiNrD4UyT0JSz | -OJ_PU-ftGPy7TovEc5a |  | 379971 | 370858 |  |  |  |  | 19'-4" | 24'-7" | 12 | 6 | reference
| (I)nstalling | CPS Energy | 379966 | 45-4 | NO | YES (1) | 89.74% |  | -OJ_PUnagFevyxyI1UKq | -OJ_PU-d5b_qyvPLb1ox | -OJ_PUnb9V2J9IPn2-Mw |  | 379966 | 379971 |  |  |  |  | 18'-8" | 23'-9" | 9 | 12 | reference
| (E)xisting | CPS Energy | 373937 | 55-3 Southern Pine | NO | YES (1) |  | C | -OJ_P_8Z7s5gxN9tQia9 | -OJ_PUnagFevyxyI1UKq | -OJ_P_8_5zjTkFGS5bHB |  | 373937 | 379966 |  |  |  |  | 22'-3" | 31'-3" | 8 | 9 | reference
| (E)xisting | CPS Energy | 404475 | 55-3 Southern Pine | NO | YES (1) | 78.54% | C | -OJ_PcyozaoP6NUp-j7U | -OJ_P_8Z7s5gxN9tQia9 | -OJ_PcyptnRey_Z82GXx |  | 404475 | 373937 |  |  |  |  | 28'-8" | 36'-5" | 7 | 8 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJ_PfpGg-tghpr8rduu | -OJ_PcyozaoP6NUp-j7U | -OJ_PfpI089rhm2JQKZ8 |  | N/A | 404475 | [6 empty] | N/A | 7 | service drop
| (E)xisting | CPS Energy | 373935 | 45-4 | YES (1) | YES (1) | 80.86% |  | -OJ_Q5tV9V_pOdD7pb8_ | -OJ_PcyozaoP6NUp-j7U | -OJ_Q5tXST15Fpt06P9Y |  | 373935 | 404475 |  |  |  |  | 15'-3" | 30'-10" | 8 | 7 | reference
| (I)nstalling | CPS Energy | 398490 | 50-1 Southern Pine | NO | NO | 51.03% | B | -OJ_Q7NcUVlDc3XciFjR | -OJ_Q5tV9V_pOdD7pb8_ | -OJ_Q7NdwR-v3jPk-b_R |  | 398490 | 373935 |  |  |  |  | 17'-5" | 25'-4" | 7 | 8 | reference
| (I)nstalling | CPS Energy | 900997 | 45-2 Southern Pine | NO | YES (2) | 64.17% | C | -OJ_QBhaCD9_C4-gzvKc | -OJ_Q7NcUVlDc3XciFjR | -OJ_QBhbb_WLtq3Ka9s6 |  | 900997 | 398490 |  |  |  |  | 21'-0" | 26'-5" | 5 | 7 | reference | Make Ready Complex
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJ_QCSLlpz2-ePrCvai | -OJ_QBhaCD9_C4-gzvKc | -OJ_QCSMyGZH7f6I9o0n |  | N/A | 900997 | [6 empty] | N/A | 5 | service drop
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJ_QIPG9V_pOdD7pb8_ | -OJ_QBhaCD9_C4-gzvKc | -OJ_QIPHST15Fpt06P9Y |  | N/A | 900997 | [6 empty] | N/A | 5 | service drop
| (I)nstalling | CPS Energy | PL404474 | 40-3 Southern Pine | NO | NO | 62.45% | C | -OJ_QKaoQC9V_pOdD7pb | -OJ_QBhaCD9_C4-gzvKc | -OJ_QKap8_9w_POuOX7d |  | PL404474 | 900997 |  |  |  |  | 19'-6" | 25'-6" | 4 | 5 | aerial cable | Make Ready Simple
| (I)nstalling | CPS Energy | 398491 | 45-2 Southern Pine | NO | YES (2) | 61.49% | C | -OJ_QN1ZoFM8EVIZXesW | -OJ_QLUJ-TR4p9hLQz72 | -OJ_QN1_yILRwv5lKaw7 |  | 398491 | 401451 |  |  |  |  | 15'-1" | 24'-8" | 2 | 3 | reference | Make Ready Simple
| (I)nstalling | CPS Energy | 410620 | 40-4 | NO | NO | 82.20% |  | -OJ_QO1-g_v02hBjKOt6 | -OJ_QN1ZoFM8EVIZXesW | -OJ_QO10emfZauaNUM4I |  | 410620 | 398491 |  |  |  |  | 14'-10" | 25'-8" | 1 | 2 | aerial cable | Make Ready Simple
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJ_QOWgDX_T_o2mDHgm | -OJ_QO1-g_v02hBjKOt6 | -OJ_QOWhqMHh5FyZwRjX |  | N/A | 410620 |  |  |  |  | 14'-5" | 27'-1" | N/A | 1 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJ_Q_2zQC9V_pOdD7pb | -OJ_QN1ZoFM8EVIZXesW | -OJ_Q_30y6ST15Fpt06P |  | N/A | 398491 | [6 empty] | N/A | 2 | service drop
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJicpxLlJrt3UH71TWO | -OJ_QN1ZoFM8EVIZXesW | -OJicpxMFYxWgBnSp-u6 |  | N/A | 398491 |  |  |  |  | 10'-2" |  | N/A | 2 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJidRLlRxqQeggQtXCK | -OJ_QN1ZoFM8EVIZXesW | -OJidRLmSEKlA8hR3NTs |  | N/A | 398491 | [6 empty] | N/A | 2 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJif9T_nMiNLnIatkCE | -OJif6kQEblo9j4gD6-l | -OJif9TaTKzDx4iAqQeV |  | N/A | 389359 | [6 empty] | N/A | 3 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJiwnufSPtvM_NoHu-b | -OJ_QBhaCD9_C4-gzvKc | -OJiwnugdivKBvbKlEws |  | N/A | 900997 | [6 empty] | N/A | 5 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJizUfB6H37u6SrK1l9 | -OJ_PcyozaoP6NUp-j7U | -OJizUfCbgskwirleI6V |  | N/A | 404475 | [5 empty] | 29'-5" | N/A | 7 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJizVhsWFAJTepAa5_c | -OJ_PcyozaoP6NUp-j7U | -OJizVhtXFup-FvgxVDv |  | N/A | 404475 | [5 empty] | 21'-1" | N/A | 7 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj-3rquPvao-Sn6zeB | -OJ_PcyozaoP6NUp-j7U | -OJj-3rr4m-8Bk_2D0uu |  | N/A | 404475 | [6 empty] | N/A | 7 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj-FTw6Wn0_-OfbWAR | -OJ_PcyozaoP6NUp-j7U | -OJj-FTw6Wn0_-OfbWAS |  | N/A | 404475 | [6 empty] | N/A | 7 | down guy
| (E)xisting |  | PL401450 |  | NO | NO | 91.71% |  | -OJj-TXvWyjgsyrmLNbB | -OJ_PcyozaoP6NUp-j7U | -OJj-TXvWyjgsyrmLNbC |  | PL401450 | 404475 | [6 empty] | 11 | 7 | overhead guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj0OsdLUpBwiuyw4c7 | -OJ_P_8Z7s5gxN9tQia9 | -OJj0Ose1XyGGFWMB044 |  | N/A | 373937 | [6 empty] | N/A | 8 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj1aunXfwu-9jVz-yL | -OJ_P_8Z7s5gxN9tQia9 | -OJj1aunXfwu-9jVz-yM |  | N/A | 373937 | [6 empty] | N/A | 8 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj2DSZYYI4992do4SG | -OJ_P_8Z7s5gxN9tQia9 | -OJj2DSZYYI4992do4SH |  | N/A | 373937 | [6 empty] | N/A | 8 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OJj2q6jHK_EzpyUmjhZ | -OJ_P_8Z7s5gxN9tQia9 | -OJj2q6kUMzRpTvFaeiA |  | N/A | 373937 | [6 empty] | N/A | 8 | down guy
| (I)nstalling | CPS Energy | 389359 | 45-4 Southern Pine | YES (1) | YES (2) | 92.00% | D | -OJif6kQEblo9j4gD6-l | -OJ_QKaoQC9V_pOdD7pb | -OJxyAJpFgj-CaetpYWz |  | 389359 | PL404474 |  |  |  |  | 17'-8" | 22'-8" | 3 | 4 | aerial cable
| (E)xisting | CPS Energy | 401451 | 40-4 | NO | YES (1) | 95.28% |  | -OJ_QLUJ-TR4p9hLQz72 | -OJif6kQEblo9j4gD6-l | -OJxyBFvYWzC2pHGlG4t |  | 401451 | 389359 |  |  |  |  | 18'-5" | 25'-6" | 3 | 3 | reference
| (E)xisting |  | N/A |  | NO | NO |  |  | -ONthXWxHg2F_kwEDXrP | -OJ_PMjpiNrD4UyT0JSz | -ONthXX-ClOLypfLM3eG |  | N/A | 370858 |  |  |  |  | 20'-8" | 26'-5" | N/A | 6 | aerial cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOZIxBNMakHJSvemleq | -OJ_QBhaCD9_C4-gzvKc | -OOZIxBTFE8ctJ5d0c0I |  | N/A | 900997 | [6 empty] | N/A | 5 | underground cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOZNWx7_kwEDXrPEvVn | -OJ_PMjpiNrD4UyT0JSz | -OOZNWxAypfLM3eGmttF |  | N/A | 370858 | [6 empty] | N/A | 6 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOZUW2bGlyCTgzI09QP | -OJ_PUnagFevyxyI1UKq | -OOZUW2dlELULUqxUfD9 |  | N/A | 379966 | [6 empty] | N/A | 9 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOc-dXIfLM3eGmttFF_ | -OJ_QN1ZoFM8EVIZXesW | -OOc-dXKJSvemleqjx1G |  | N/A | 398491 | [6 empty] | N/A | 2 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOc-pwgClOLypfLM3eG | -OJ_QBhaCD9_C4-gzvKc | -OOc-pwjeqjx1GazxpjG |  | N/A | 900997 | [6 empty] | N/A | 5 | down guy
|  |  | 389359 | [5 empty] | -OJif6kQEblo9j4gD6-l | -OJ_QN1ZoFM8EVIZXesW | -OP2M3Yf2DfJczUNfA6w |  | 389359 | 398491 | [6 empty] | 3 | 2 | underground cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OP7d1PBo-zJXbBSF6BB | -OJif6kQEblo9j4gD6-l | -OP7d1PFsI90KP-5JyK6 |  | N/A | 389359 | [6 empty] | N/A | 3 | down guy
| (I)nstalling | CPS Energy | 370858 | 45-2 Southern Pine | NO | YES (1) | 41.95% | C | -OJ_PMjpiNrD4UyT0JSz | -OOZJCyPmttFF_XEZ39P | -OPCjr3oYEEY70EImQWq |  | 370858 | N/A | [6 empty] | 6 | N/A | underground cable | Make Ready Simple
| (E)xisting |  | N/A |  | NO | NO |  |  | -OPClUfHjS4CexIygstA | -OOZIxBNMakHJSvemleq | -OPClUfJOEDoYY5dPYgp |  | N/A | N/A | [6 empty] | N/A | N/A | underground cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OPCo_ePXdIpGo8ImGP1 | -OPClUfHjS4CexIygstA | -OPCo_eQjlrp6iqpWvf_ |  | N/A | N/A | [6 empty] | N/A | N/A | underground cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OPG6ld2hXG0QGzOKIQB | -OJ_P_8Z7s5gxN9tQia9 | -OPG6ld8ECwVIVEO3OuE |  | N/A | 373937 | [6 empty] | N/A | 8 | down guy
| (E)xisting |  | N/A |  | NO | NO |  |  | -OPGEz57QWmw6gwuDYpS | -OPCo_ePXdIpGo8ImGP1 | -OPGEz57QWmw6gwuDYpT |  | N/A | N/A | [6 empty] | N/A | N/A | underground cable
| (E)xisting |  | N/A |  | NO | NO |  |  | -OOZJCyPmttFF_XEZ39P | -OPGEz57QWmw6gwuDYpS | -OPGF38Z3hCfh6dScw0O |  | N/A | N/A | [6 empty] | N/A | N/A | underground cable